## 联网状况
| 站位 | 设备 | MES网络IP地址 | 设备联网日期 | Ping from 10.233.121.65 | Ping from 10.233.121.54 | Ping from 10.233.108.153 | 备注
FOL | Substrate Mount | PK27 | 10.233.132.71 | 2025-12-17 | X | X | O
FOL | Substrate Mount Cover Attach | KM04 | 10.233.132.72 | 2025-12-15 | O | O | O
FOL | Substrate Mount Carrier Map | MC01 | 10.233.132.73 | 2025-12-15 | O | O | O
SUB | Bump Bond | BBA9 | 10.233.132.51 | 2025-12-18 | X | X | X
SUB | Wafer Cleaning | DC07 | 10.233.132.52 | 2025-12-15 | O | O | O
SUB | Wafer AVI | WB01 | 10.233.132.53 | Pending |  |  |  | 和AV，DB共用设备，需讨论连接MES后如何处理旧机种数据源
SUB | Wafer UV Irradiation | UV02 | 10.233.132.54 | 2025-12-17 | X | X | X | Offline
FOL | FCB Inline Plasma Cleaning | PC62 | 10.233.132.55 | 2025-12-15 | X | X | O
FOL | FCB Inline Flip Chip Bond | FCA8 | 10.233.132.56 | 2025-12-15 | O | O | O
FOL | FCB Inline Under Fill | JDA8 | 10.233.132.57 | 2025-12-16 | X | X | O
FOL | FOL Inline Sensor Cleaning | HFB8 | 10.233.132.58 | 2025-12-12 | X | X | O
FOL | FOL Inline Particle Picker | SC01 | 10.233.132.59 | 2025-12-16 | X | X | O
FOL | FOL Inline Glass Attach + UV cure | FHA7 | 10.233.132.60 | 2025-12-16 | X | X | O
FOL | DT&IRCF PP Inline Dust Trap | FH60 | 10.233.132.61 | 2025-12-15 | O | O | O
FOL | DT&IRCF PP Inline IRCF Particle picker | TWA2 | [5 empty] | SEA C4
FOL | DT&IRCF PP Inline Cover Remover | KR07 | 10.233.132.62 | 2025-12-16 | X | X | O
SUB | VCM Inline 1+2 VCM Flipping | TBD | 10.233.132.63 | pending |  |  |  | VCM Inline设备setup中
SUB | VCM Inline 1+2 Plasma Cleaning | GF09 | 10.233.132.64 | 2025-12-18 | O | O | O
SUB | VCM Inline 1+2 VCM Air Blow | CV15 | 10.233.132.65 | pending |  |  |  | VCM Inline设备setup中
SUB | VCM Barrel Assy(Pre-Focus) | TBD |  | pending |  |  |  | VCM Inline设备setup中 | 12
SUB | VCM Inline 1+2 Plasma Cleaning | GF08 | 10.233.132.66 | pending |  |  |  | VCM Inline设备setup中
SUB | VCM Inline 1+2 VCM Flipping | TBD | 10.233.132.67 | pending |  |  |  | VCM Inline设备setup中
SUB | VCM Inline 1+2 VCM Air Blow | CV16 | 10.233.132.68 | pending |  |  |  | VCM Inline设备setup中
FOL | Active Alignment Active Alignment | AAD4 | 10.233.132.69 | pending |  |  |  | 设备dri要求获取设备文档
EOL | Cube Transfer | TC19 | 10.233.132.70 | 2025-12-16 | O | O | O
EOL | AF Soldering (2 tray) | LSN5 | 10.233.148.51 | 2025-12-19 | O | O | O
EOL | AF AVI | TBD | 10.233.148.52 |  |  |  |  | SEA C4
EOL | ACF(Full-auto) ACF Full Auto | AF20 | 10.233.148.53 | 2025-12-19 | O | O | O
EOL | EOL Inline Stiffener attach | SB13 | 10.233.148.54 | 2025-12-19 | X | X | O
EOL | EOL Inline Flex reinforcement & Stiffener Sidefill | CK26 | 10.233.148.55 | 2025-12-19 | O | O | O
EOL | Laser Mark Laser Mark | MA29 | 10.233.148.56 | 2025-12-19 | O | O | O
EOL | AVI&Cap Attach AVI & Cap Attach(6side) | VAA2 | 10.233.140.51 | 2025-12-19 | X | X | O
TEST | Up Test MFG | TBD
TEST | Down test MFG | YD57 | ？ | 病毒扫描中 | ? |  | ?
TEST | ASPC MFG | AT50 | ？ | 病毒扫描中 | ? |  | ?
TEST | Up Test OQC | TBD
TEST | Down test OQC | YD59
TEST | ASPC OQC | AT60
TEST | Flare test OQC | TBD
| Collation of marking | TBD

## secsgem测试
SEA | Sub Process/station | Main Process/station | Machine | Vendor | MES communication | SEA C5.0设备 | MES IP地址 | 略称 | CarrierMap | 基础开发 | 连通性测试
FOL |  | Substrate mount | Substrate Mount | Yamaha | TBD | PK27 | 10.233.132.71
FOL |  |  | Substrate Mount Cover Attach | Nutek | SECS/GEM | KM04 | 10.233.132.72 | KM |  | ○
FOL |  |  | Substrate Mount Carrier Map | S-Takaya | SECS/GEM | MC01 | 10.233.132.73 | MC | ○ | ○
FOL | Bump bonding |  | Bump Bond | K&S | SECS/GEM | BBA9 | 10.233.132.51 | BB |  | ○
FOL | Wafer cleaning |  | Wafer Cleaning | Disco | SECS/GEM | DC07 | 10.233.132.52 | DC |  | ○
FOL | Wafer AVI |  | Wafer AVI | Camtek | Log | WB01 | 10.233.132.53
FOL | Wafer UV |  | Wafer UV Irradiation | Lintec | SECS/GEM | UV02 | 10.233.132.54 | UV |  | ○ | ○
FOL |  | AR plasma | FCB Inline Plasma Cleaning | Nordson | SECS/GEM | PC62 | 10.233.132.55 | PC |  | ○ | ○
FOL |  | FCB | FCB Inline Flip Chip Bond | TDK | SECS/GEM | FCA8 | 10.233.132.56 | FC | ○ | ○ | ○
FOL |  | UF | FCB Inline Under Fill | Besi | SECS/GEM | JDA8 | 10.233.132.57 | JD | ○ | ○ | 12/19 X | 机台Host互相无法Ping通
FOL |  | Sensor Cleaning | FOL Inline Sensor Cleaning | LG | SECS/GEM | HFB8 | 10.233.132.58 | HF |  | ○
FOL |  | Sensor PP | FOL Inline Particle Picker | ASM | SECS/GEM | TBD | 10.233.132.59 | PP | ○ | ？ |  | 据称与LH一致，因此CopyLH处理代码，机台Setup中暂时无法确认
FOL |  | GA | FOL Inline Glass Attach + UV cure | Besi | SECS/GEM | FHA7 | 10.233.132.60 | GA | ○ | ○ | ○
FOL |  | DT | DT&IRCF PP Inline Dust Trap | PFA | SECS/GEM | FH60 | 10.233.132.61 | DT | ○ | ○ | ○
FOL |  | IRCF PP | DT&IRCF PP Inline IRCF Particle picker | ASM | SECS/GEM | TWA2 |  | IRCFPP | ○ | ○ |  | SEA C4.0
FOL |  | Top carrier remove | DT&IRCF PP Inline Cover Remover | Nutek | SECS/GEM | KR01 | 10.233.132.62 | KR |  | ○
FOL |  | AA | Active Alignment Active Alignment | ASM | DLL | AAD4 | 10.233.132.63 | AA | ○
FOL | 1st Flip tray |  | VCM Inline 1+2 VCM Flipping | WST | SECS/GEM | TBD | 10.233.132.64 | FT1 |  | ○
FOL | 1st Plasma |  | 1st Plasma | Nordson | Log | GF09 | 10.233.132.65
FOL | 1st BS |  | VCM Inline 1+2 VCM Air Blow | KumKang(WST) | SECS/GEM | CV15 |  | BS1 |  | ○
FOL | Pre-Focus |  | Pre-Focus | HVS | DLL | TBD | 10.233.132.66
FOL | 2nd Flip tray |  | VCM Inline 1+2 VCM Flipping | WST | SECS/GEM | TBD | 10.233.132.67 | FT2 |  | ○
FOL | 2nd plasma |  | 2nd plasma | Nordson | Log | GF08 | 10.233.132.68 |  |  | ○
FOL | 2nd BS |  | VCM Inline 1+2 VCM Air Blow | KumKang(WST) | SECS/GEM | CV16 | 10.233.132.69 | BS2 |  | ○
EOL |  | Cube Transfer | Cube Transfer | ASM | Log | TC19 | 10.233.132.70
EOL |  | AF laser soldering | AF Soldering (2 tray) | Horiuchi | SECS/GEM | LSN5 | 10.233.148.51 | LS |  | ○
EOL |  | AF AVI From C4.0 | AF AVI | WST(Musashi) | SECS/GEM | TBD | 10.233.148.52 | AFAVI |  |  |  | SEA C4.0
EOL |  | ACF | ACF(Full-auto) ACF Full Auto | Ohashi | SECS/GEM | AF20 | 10.233.148.53 | AF |  | ○
EOL |  | SA | EOL Inline Stiffener attach | Tosa | SECS/GEM | SB13 | 10.233.148.54 | SB |  | ○
EOL |  | FR vs SS | EOL Inline Flex reinforcement & Stiffener Sidefill | Tosa | SECS/GEM | CK26 | 10.233.148.55 | CK |  | ○
EOL |  | Laser marking | Laser Mark Laser Mark | S-Takaya | SECS/GEM | MA29 | 10.233.148.56 | LM |  | ○ | ○
EOL |  | AVI+CA | AVI&Cap Attach AVI & Cap Attach(6side) | Sharp(Twist) | SECS/GEM | VAA2 | 10.233.140.51 | VA |  | ○
PA | Sub Process/station | Main Process/station | Machine | Vendor | MES communication | PA设备 | 当前网络(GCM)IP地址 | 略称 | CarrierMap | 基础开发 | 连通性测试
FOL | Lens Plasma |  | Lens Plasma | YKT（Panasonic） | SECS/GEM | PC10 | 新设备 | PC |  | ○ | 12/12 X | 机台通信IP地址无法变更，Vendor确认中
[9 empty] | 基础开发= | 连通性
状态
远程停机